## Slide 1
Day 48 of 60
FFIC Approvals on time
Project Update Dashboard – Government Approvals
Project Objective:
Project Time:
Project Risks:
Project Updates:
Next Steps:
Secure necessary government approvals to proceed with SoliD's platform and services.
Currently Day 48 out of 60 business days. The project started on April 1 and is scheduled to finish within the next two weeks.
Approvals received from FFIC and documents are now heading to the Verification Office.
Completed tasks: Items #220, 221, 224, 225, 226.
Delays: Tasks #222 and #223 are behind schedule and may not be completed by tomorrow.
Behind on 3 tasks this week, and next week’s milestone may be affected by staff availability (Faz will be out of town).
$6,200 over budget due to waiver fees and overtime from delays. Risk of further budget overruns if extensions are needed.
  Complete remaining tasks and file for extensions next week if necessary.
  Monitor budget closely and provide regular updates.

## Slide 2
Iteration 4
Next Product Release: Tomorrow
Project Update Dashboard – Mobile App
Project Objective:
Project Time:
Project Updates:
Project Risks:
Project Next Steps:
The app is progressing as planned, with several features in development and some bugs being addressed. The project timeline is on track for the initial app release.
Launch a simple, modern phone app to raise awareness for SoliD’s upcoming services. .
The app's basic features are in place, with early feedback being integrated.
Recent issues found in the app could potentially delay the release if not addressed promptly.
Finalize bug fixes and conduct thorough testing before the initial app release.